## Sheet1
Issue Key | Issue Summary | Time spent | Started at | Updated at | Comment | Author | Author's Account Id | Project Key | Project Name | Components | Labels | Epic Key | Epic Name | Epic Summary | Issue Type | Time Spent (seconds) | Original Estimate | Original Estimate (seconds) | Remaining Estimate | Remaining Estimate (seconds) | Due Date | Parent Key | Parent Summary
BIL-306 | Technical Design | 0.5 | 2019-12-04T09:30:00+05:30 | 2019-12-12T18:27:28+05:30 |  | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 |  | 0 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-261 | UTR Setting and Charges Module | 7.5 | 2019-12-04T10:00:00+05:30 | 2019-12-12T18:28:43+05:30 | form design, fetch data, save data, show history, | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | UTR |  | BIL-22 | UTR Setting | UTR Setting | Story | 27000 | 3d 6h 4m | 108240 | 0m | 0 | 2019-12-11 | BIL-261 | UTR Setting and Charges Module
BIL-256 | Change in LOI Entry Module | 7 | 2019-12-04T10:00:00+05:30 | 2019-12-07T23:52:15+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  | BIL-12 | LOI Entry | LOI Entry | Story | 25200 | 2d 3h | 68400 | 1d 2h | 36000 | 2019-12-11 | BIL-256 | Change in LOI Entry Module
BIL-267 | Coding+UT | 7.42 | 2019-12-04T10:30:00+05:30 | 2019-12-05T13:08:18+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 26700 | 2d | 57600 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-413 | On 'Vendor Registration' page, the heading 'General Info', 'Accounts Details' should be shown in Form Legend. | 1 | 2019-12-04T17:44:00+05:30 | 2019-12-19T09:44:17+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-275 | Coding+UT | 1 | 2019-12-05T01:57:00+05:30 | 2019-12-19T09:58:06+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-261 | UTR Setting and Charges Module | 3.5 | 2019-12-05T09:00:00+05:30 | 2019-12-06T16:45:55+05:30 | update utr charges, other change in utr | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | UTR |  | BIL-22 | UTR Setting | UTR Setting | Story | 12600 | 3d 6h 4m | 108240 | 0m | 0 | 2019-12-11 | BIL-261 | UTR Setting and Charges Module
BIL-256 | Change in LOI Entry Module | 2 | 2019-12-05T13:53:00+05:30 | 2019-12-18T16:37:12+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  | BIL-12 | LOI Entry | LOI Entry | Story | 7200 | 2d 3h | 68400 | 1d 2h | 36000 | 2019-12-11 | BIL-256 | Change in LOI Entry Module
BIL-415 | Admin should be assigned the privilege to approve and reject the form. | 1 | 2019-12-05T17:45:00+05:30 | 2019-12-19T09:45:35+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-267 | Coding+UT | 7 | 2019-12-06T05:25:00+05:30 | 2019-12-26T12:26:33+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 25200 | 2d | 57600 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-275 | Coding+UT | 1 | 2019-12-06T14:58:00+05:30 | 2019-12-19T09:58:26+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-275 | Coding+UT | 1 | 2019-12-06T17:03:00+05:30 | 2019-12-19T10:03:44+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-275 | Coding+UT | 7 | 2019-12-07T12:05:00+05:30 | 2019-12-12T18:05:26+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 25200 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-272 | Release Management | 0.8 | 2019-12-09T09:30:00+05:30 | 2019-12-25T23:03:54+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 2880 | 18m | 1080 | 12m | 720 |  | BIL-256 | Change in LOI Entry Module
BIL-264 | Add Mulitiple Bank Account Details For SLDC | 7 | 2019-12-09T09:31:00+05:30 | 2019-12-09T17:39:24+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  | BIL-6 | Vendor Registration | Vendor Registration | Story | 25200 | 3d 3m | 86580 | 0m | 0 | 2019-12-18 | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-341 | Estimation | 2 | 2019-12-09T10:00:00+05:30 | 2019-12-13T18:44:38+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-257 | Manage Contract and Application Summary
BIL-349 | Coding+UT | 1 | 2019-12-09T10:30:00+05:30 | 2019-12-10T11:21:00+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 |  | 0 | 0m | 0 |  | BIL-346 | Bilateral-Tally Integration
BIL-271 | Project Management | 0.17 | 2019-12-09T11:30:00+05:30 | 2019-12-10T11:27:44+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 18m | 1080 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-279 | Project Management | 0.17 | 2019-12-09T11:30:00+05:30 | 2019-12-10T11:26:48+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 30m | 1800 | 0m | 0 |  | BIL-255 | Client Registration
BIL-299 | Coding+UT | 4 | 2019-12-09T13:30:00+05:30 | 2019-12-26T17:30:44+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 1d | 28800 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges
BIL-257 | Manage Contract and Application Summary | 1 | 2019-12-09T14:30:00+05:30 | 2019-12-09T18:03:15+05:30 | Remove Extra inputs at the time of LOI addition in existing Contract | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | Manage Contract |  | BIL-18 | Contract Manangement | Contract Manangement | Story | 3600 | 1d 5h 8m | 47280 | 0m | 0 | 2019-12-17 | BIL-257 | Manage Contract and Application Summary
BIL-268 | Code Review | 2 | 2019-12-09T16:35:00+05:30 | 2019-12-13T18:36:10+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 1h 36m | 5760 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-309 | Estimation | 2 | 2019-12-09T16:43:00+05:30 | 2019-12-13T18:43:09+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-340 | Code Review | 2 | 2019-12-09T16:46:00+05:30 | 2019-12-13T18:46:36+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 48m | 2880 | 0m | 0 |  | BIL-257 | Manage Contract and Application Summary
BIL-264 | Add Mulitiple Bank Account Details For SLDC | 2 | 2019-12-10T09:16:00+05:30 | 2019-12-10T11:16:39+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  | BIL-6 | Vendor Registration | Vendor Registration | Story | 7200 | 3d 3m | 86580 | 0m | 0 | 2019-12-18 | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-284 | Code Review | 2 | 2019-12-10T10:00:00+05:30 | 2019-12-13T18:59:02+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 1h 36m | 5760 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-285 | Estimation | 2 | 2019-12-10T10:00:00+05:30 | 2019-12-13T18:48:01+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-354 | To check that the Document will be Uploaded before the entry of LOI information | 0.17 | 2019-12-10T10:56:00+05:30 | 2019-12-27T13:12:02+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-307 | Coding+UT | 1.5 | 2019-12-10T11:00:00+05:30 | 2019-12-12T17:58:04+05:30 | utr charges setting on saving or updating data | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 5400 | 2d 4h | 72000 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-311 | Project Management | 0.17 | 2019-12-10T11:27:53+05:30 | 2019-12-10T11:27:55+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 18m | 1080 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-357 | To check that as soon as the client is selected, the details of clients are shown. | 0.17 | 2019-12-10T14:57:00+05:30 | 2019-12-27T13:13:14+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-359 | To check what happens when document is uploaded but LOI information is not filled. | 0.17 | 2019-12-10T14:58:00+05:30 | 2019-12-27T13:13:39+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-370 | project management | 1 | 2019-12-10T15:00:00+05:30 | 2019-12-11T12:01:30+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 1h 24m | 5040 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-275 | Coding+UT | 3 | 2019-12-10T15:03:00+05:30 | 2019-12-11T18:03:48+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 10800 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-358 | To check that document can be uploaded only when document type is selected. | 0.17 | 2019-12-10T15:07:00+05:30 | 2019-12-27T13:13:29+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-353 | To check that there is an option to upload Document before the entry of LOI information. | 0.17 | 2019-12-10T15:30:00+05:30 | 2019-12-27T13:11:49+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-356 | To check that the file uploaded can be viewed in sidebar. | 0.17 | 2019-12-10T15:56:00+05:30 | 2019-12-27T13:12:57+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-255 | Client Registration | 2 | 2019-12-10T16:05:00+05:30 | 2019-12-11T18:05:22+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  | BIL-8 | All Vendor | All Vendor | Story | 7200 | 1w 1d 48m | 175680 | 0m | 0 | 2019-12-16 | BIL-255 | Client Registration
BIL-360 | To check that there is modifcation in energy types. | 0.17 | 2019-12-10T16:20:00+05:30 | 2019-12-27T13:13:48+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-257 | Manage Contract and Application Summary | 2 | 2019-12-10T16:30:00+05:30 | 2019-12-12T17:59:12+05:30 | check code for merge list | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | Manage Contract |  | BIL-18 | Contract Manangement | Contract Manangement | Story | 7200 | 1d 5h 8m | 47280 | 0m | 0 | 2019-12-17 | BIL-257 | Manage Contract and Application Summary
BIL-285 | Estimation | 2 | 2019-12-10T16:51:00+05:30 | 2019-12-13T18:50:55+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-367 | estimation | 2 | 2019-12-10T17:00:00+05:30 | 2019-12-11T12:27:01+05:30 | Making estimation…. | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-355 | To check the file types allowed to upload for different document type. | 0.17 | 2019-12-10T17:56:00+05:30 | 2019-12-27T13:12:38+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 600 |  | 0 | 10m | 600
BIL-270 | QA Testing | 2.3 | 2019-12-10T18:16:00+05:30 | 2019-12-27T13:10:31+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 8280 | 5h 18m | 19080 | 1d | 28800 |  | BIL-256 | Change in LOI Entry Module
BIL-312 | Release Management | 0.1 | 2019-12-10T22:54:00+05:30 | 2019-12-25T23:08:53+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 360 | 18m | 1080 | 12m | 720 |  | BIL-261 | UTR Setting and Charges Module
BIL-367 | estimation | 1 | 2019-12-11T10:00:00+05:30 | 2019-12-13T19:11:49+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 |  | 0 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-293 | Estimation | 2 | 2019-12-11T10:00:00+05:30 | 2019-12-13T19:04:34+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-308 | Code Review | 2 | 2019-12-11T10:00:00+05:30 | 2019-12-13T18:40:14+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 2h | 7200 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-261 | UTR Setting and Charges Module | 1.5 | 2019-12-11T11:00:00+05:30 | 2019-12-12T18:05:02+05:30 | add intra state application fee in utr charge settings, alter table utr setting state | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | UTR |  | BIL-22 | UTR Setting | UTR Setting | Story | 5400 | 3d 6h 4m | 108240 | 0m | 0 | 2019-12-11 | BIL-261 | UTR Setting and Charges Module
BIL-346 | Bilateral-Tally Integration | 1 | 2019-12-11T11:00:00+05:30 | 2019-12-11T18:53:30+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Story | 3600 |  | 0 | 0m | 0 |  | BIL-346 | Bilateral-Tally Integration
BIL-310 | QA Testing | 7 | 2019-12-11T11:06:00+05:30 | 2020-01-03T18:19:09+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 25200 | 6h 36m | 23760 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-275 | Coding+UT | 4 | 2019-12-11T12:13:00+05:30 | 2019-12-12T18:01:35+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-299 | Coding+UT | 5.25 | 2019-12-11T14:16:00+05:30 | 2019-12-26T17:23:06+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 18900 | 1d | 28800 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges
BIL-377 | Project Review 01 Dec 2019 to 10 Dec 2019 | 3 | 2019-12-11T15:00:00+05:30 | 2019-12-11T18:56:33+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | Project Review |  |  |  |  | Task | 10800 | 1h | 3600 | 0m | 0 | 2019-12-11
BIL-289 | Impact Analysis | 2 | 2019-12-11T17:08:00+05:30 | 2019-12-13T19:08:49+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 2h 36m | 9360 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-351 | Project Management | 0.5 | 2019-12-11T17:26:00+05:30 | 2019-12-13T17:26:29+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 |  | 0 | 0m | 0 |  | BIL-346 | Bilateral-Tally Integration
BIL-303 | Project Management | 0.17 | 2019-12-11T17:29:00+05:30 | 2019-12-13T17:29:47+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 1h | 3600 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges
BIL-280 | Release Management | 0.1 | 2019-12-11T22:50:00+05:30 | 2019-12-25T22:57:32+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 360 | 30m | 1800 | 24m | 1440 |  | BIL-255 | Client Registration
BIL-368 | coding+ut | 8 | 2019-12-12T09:30:00+05:30 | 2019-12-17T10:51:07+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 | 2d 30m | 59400 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-337 | Impact Analysis | 0.5 | 2019-12-12T09:30:00+05:30 | 2019-12-12T18:39:16+05:30 |  | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 1h 12m | 4320 | 0m | 0 |  | BIL-257 | Manage Contract and Application Summary
BIL-267 | Coding+UT | 1 | 2019-12-12T10:00:00+05:30 | 2019-12-13T19:16:31+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 2d | 57600 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-275 | Coding+UT | 3 | 2019-12-12T10:00:00+05:30 | 2019-12-13T19:13:24+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 10800 | 4d | 115200 | 0m | 0 |  | BIL-255 | Client Registration
BIL-269 | Estimation | 2 | 2019-12-12T10:00:00+05:30 | 2019-12-13T18:31:12+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-257 | Manage Contract and Application Summary | 7 | 2019-12-12T10:30:00+05:30 | 2019-12-12T18:34:53+05:30 | merge other buyer seller details in one table | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | Manage Contract |  | BIL-18 | Contract Manangement | Contract Manangement | Story | 25200 | 1d 5h 8m | 47280 | 0m | 0 | 2019-12-17 | BIL-257 | Manage Contract and Application Summary
BIL-278 | QA Testing | 4 | 2019-12-12T10:41:00+05:30 | 2020-01-03T18:16:02+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 1d 2h 36m | 38160 | 2h | 7200 |  | BIL-255 | Client Registration
BIL-385 | To check that Billing Frequency is Set. | 0.08 | 2019-12-12T11:00:00+05:30 | 2020-01-03T18:14:33+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 300 |  | 0 | 15m | 900
BIL-386 | To check that On Submission of LOI , Email Body will Contain the LOI Summary and if LOI is Approved on Email the LOI Status will be marked as APPROVED(Email) | 0.08 | 2019-12-12T11:30:00+05:30 | 2020-01-03T18:14:47+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 300 |  | 0 | 15m | 900
BIL-370 | project management | 1.5 | 2019-12-12T12:00:00+05:30 | 2019-12-13T17:20:34+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 5400 | 1h 24m | 5040 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-279 | Project Management | 0.17 | 2019-12-12T13:00:00+05:30 | 2019-12-13T17:25:21+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 30m | 1800 | 0m | 0 |  | BIL-255 | Client Registration
BIL-366 | impact analysis | 0.1 | 2019-12-12T13:30:00+05:30 | 2019-12-28T06:14:00+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 360 | 2h 36m | 9360 | 2h 30m | 9000 |  | BIL-361 | revenue data in LMS sheet
BIL-351 | Project Management | 0.25 | 2019-12-12T13:30:00+05:30 | 2019-12-13T17:26:47+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 900 |  | 0 | 0m | 0 |  | BIL-346 | Bilateral-Tally Integration
BIL-311 | Project Management | 0.17 | 2019-12-12T13:30:00+05:30 | 2019-12-13T17:26:03+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 18m | 1080 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-383 | To check that mapping/linking of Import Schedule with Export Schedule is done in case of Power Swapping. | 0.08 | 2019-12-12T14:00:00+05:30 | 2020-01-03T18:14:04+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 300 |  | 0 | 15m | 900
BIL-387 | To check if the LOI details is Rejected by the Operation or Accounts Team, then BD and RM will get Notified for RE-Submit the details. | 0.08 | 2019-12-12T14:00:00+05:30 | 2020-01-03T18:15:01+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 300 |  | 0 | 15m | 900
BIL-414 | On 'Vendor Registration' page,if we click of 'Nodal Rldc Enrolled', page should open in new tab. | 0.67 | 2019-12-12T14:17:00+05:30 | 2019-12-13T15:17:36+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 2400 |  | 0 | 0m | 0
BIL-384 | To check that there is a provision to view the Billing periphery for Accounts team that will be map with Delivery Point | 0.08 | 2019-12-12T14:30:00+05:30 | 2020-01-03T18:14:18+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 300 |  | 0 | 15m | 900
BIL-295 | Project Management | 0.33 | 2019-12-12T15:00:00+05:30 | 2019-12-13T17:29:27+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1200 | 12m | 720 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-343 | Project Management | 0.33 | 2019-12-12T15:00:00+05:30 | 2019-12-13T17:28:17+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1200 | 1h | 3600 | 0m | 0 |  | BIL-257 | Manage Contract and Application Summary
BIL-412 | On 'Vendor Registration' page, if the document is not uploaded, dropdown should be hidden | 1 | 2019-12-12T15:15:00+05:30 | 2019-12-13T15:15:43+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-303 | Project Management | 0.33 | 2019-12-12T16:00:00+05:30 | 2019-12-13T17:30:33+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1200 | 1h | 3600 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges
BIL-287 | Project Management | 0.33 | 2019-12-12T16:00:00+05:30 | 2019-12-13T17:28:50+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1200 | 12m | 720 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-273 | Impact Analysis | 0.5 | 2019-12-12T16:00:00+05:30 | 2019-12-13T10:29:18+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 5h 12m | 18720 | 0m | 0 |  | BIL-255 | Client Registration
BIL-413 | On 'Vendor Registration' page, the heading 'General Info', 'Accounts Details' should be shown in Form Legend. | 1.5 | 2019-12-12T16:10:00+05:30 | 2019-12-13T15:11:27+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 5400 |  | 0 | 0m | 0
BIL-274 | Technical Design | 0.5 | 2019-12-12T16:30:00+05:30 | 2019-12-13T10:29:54+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 |  | 0 | 0m | 0 |  | BIL-255 | Client Registration
BIL-281 | Impact Analysis | 0.5 | 2019-12-12T17:00:00+05:30 | 2019-12-13T10:34:12+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 2h 36m | 9360 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-291 | Coding+UT | 4.5 | 2019-12-12T17:14:16+05:30 | 2019-12-12T19:16:21+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 16200 | 2d | 57600 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-412 | On 'Vendor Registration' page, if the document is not uploaded, dropdown should be hidden | 0.83 | 2019-12-12T17:16:00+05:30 | 2019-12-13T15:16:35+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3000 |  | 0 | 0m | 0
BIL-271 | Project Management | 0.17 | 2019-12-12T17:25:00+05:30 | 2019-12-13T17:25:41+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 600 | 18m | 1080 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-382 | To check that there is a provision to View the schedule Quantum as per LOI and at Delivery Point. | 0.08 | 2019-12-12T17:30:00+05:30 | 2020-01-03T18:13:45+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Test Case | 300 |  | 0 | 15m | 900
BIL-282 | Technical Design | 0.5 | 2019-12-12T17:30:00+05:30 | 2019-12-13T10:34:40+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 |  | 0 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-265 | Impact Analysis | 0.5 | 2019-12-12T17:47:52+05:30 | 2019-12-12T18:17:58+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 2h 36m | 9360 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-266 | Technical Design | 0.5 | 2019-12-12T17:49:27+05:30 | 2019-12-12T18:19:35+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 |  | 0 | 0m | 0 |  | BIL-256 | Change in LOI Entry Module
BIL-297 | Impact Analysis | 0.67 | 2019-12-12T18:24:28+05:30 | 2019-12-12T19:04:44+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 2400 | 1h 12m | 4320 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges
BIL-289 | Impact Analysis | 0.67 | 2019-12-12T18:25:00+05:30 | 2019-12-12T19:05:05+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 2400 | 2h 36m | 9360 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-368 | coding+ut | 8 | 2019-12-13T09:30:00+05:30 | 2019-12-17T10:51:25+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 | 2d 30m | 59400 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-416 | If the form is approved or rejected from the admin end, it should be considered as final approval. | 4 | 2019-12-13T09:42:00+05:30 | 2019-12-13T15:19:01+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 14400 |  | 0 | 0m | 0
BIL-305 | Impact Analysis | 1 | 2019-12-13T10:00:00+05:30 | 2019-12-13T18:38:13+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 3h 12m | 11520 | 0m | 0 |  | BIL-261 | UTR Setting and Charges Module
BIL-276 | Code Review | 2 | 2019-12-13T10:00:00+05:30 | 2019-12-13T17:27:47+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 3h 12m | 11520 | 0m | 0 |  | BIL-255 | Client Registration
BIL-398 | To check that Registration Approval Status is updated in LMS and in case of rejection system will allow to RE-Submit the details in LMS Portal. | 0.17 | 2019-12-13T10:46:00+05:30 | 2019-12-17T10:47:11+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 600 |  | 0 | 0m | 0
BIL-396 | To check that an email is sent to BD Team regarding RLDC Registration if the client nodal RLDC is NR, ER and NER. | 0.25 | 2019-12-13T10:48:00+05:30 | 2019-12-17T10:48:17+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-388 | To check if any Vendor Form is Pending for Approval an email and SMS is sent to RM(in CC), Accounts & Operation (in TO) | 0.25 | 2019-12-13T10:48:00+05:30 | 2019-12-17T10:48:59+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-397 | To check that Registration Form can be approved or rejected by the Accounts and Operation team. | 0.25 | 2019-12-13T10:48:00+05:30 | 2019-12-17T10:48:42+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-391 | To check that on Complete Approval of Client a notification(SMS and Email) is send to BD, Accounts and Operation Team | 0.25 | 2019-12-13T10:49:00+05:30 | 2019-12-17T10:49:47+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-389 | To check that if Form is Approved By Accounts only then the notification will send to Operation and BD team on Email | 0.25 | 2019-12-13T10:49:00+05:30 | 2019-12-17T10:49:14+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-392 | To check that there is provision required to Add Registration with RLDC, Exchange (Membership No and Date of Registration ), SLDC Registration Status | 0.25 | 2019-12-13T10:49:00+05:30 | 2019-12-17T10:50:00+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-390 | To check that if Form is Approved By Operation only then the notification will send to Finance and BD team on Email | 0.25 | 2019-12-13T10:49:00+05:30 | 2019-12-17T10:49:30+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-395 | To check that For the approval of Client Registration Form there isa Button required to View the Documents Uploaded by BD team in File Viewer. | 0.25 | 2019-12-13T10:50:00+05:30 | 2019-12-17T10:50:43+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-413 | On 'Vendor Registration' page, the heading 'General Info', 'Accounts Details' should be shown in Form Legend. | 0.25 | 2019-12-13T10:50:00+05:30 | 2019-12-17T10:50:58+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 900 |  | 0 | 0m | 0
BIL-394 | To check that Checkboxes are present on every Fields for Approval. | 0.25 | 2019-12-13T10:50:00+05:30 | 2019-12-17T10:50:31+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-393 | To check that if Client is Not Registered with Nodal RLDC then BD and Operation will Notify on Email | 0.25 | 2019-12-13T10:50:00+05:30 | 2019-12-17T10:50:15+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-398 | To check that Registration Approval Status is updated in LMS and in case of rejection system will allow to RE-Submit the details in LMS Portal. | 0.25 | 2019-12-13T10:51:00+05:30 | 2019-12-17T10:51:13+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Test Case | 900 |  | 0 | 0m | 0
BIL-261 | UTR Setting and Charges Module | 2.2 | 2019-12-13T11:02:00+05:30 | 2019-12-17T11:02:38+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | UTR |  | BIL-22 | UTR Setting | UTR Setting | Story | 7920 | 3d 6h 4m | 108240 | 0m | 0 | 2019-12-11 | BIL-261 | UTR Setting and Charges Module
BIL-255 | Client Registration | 2.17 | 2019-12-13T12:10:00+05:30 | 2019-12-13T18:11:21+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  | BIL-8 | All Vendor | All Vendor | Story | 7800 | 1w 1d 48m | 175680 | 0m | 0 | 2019-12-16 | BIL-255 | Client Registration
BIL-291 | Coding+UT | 3.5 | 2019-12-13T14:43:30+05:30 | 2019-12-13T18:14:10+05:30 | Coding+UT | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 12600 | 2d | 57600 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-415 | Admin should be assigned the privilege to approve and reject the form. | 1.5 | 2019-12-13T15:19:00+05:30 | 2019-12-13T15:19:57+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 5400 |  | 0 | 0m | 0
BIL-400 | Invalid Coding. | 0.25 | 2019-12-13T17:04:00+05:30 | 2019-12-13T17:04:56+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 900 |  | 0 | 0m | 0
BIL-406 | There is no commented out code | 0.17 | 2019-12-13T17:26:00+05:30 | 2019-12-13T17:05:43+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 600 |  | 0 | 0m | 0
BIL-404 | Every time a loi is created, it is linked with a contract. | 0.67 | 2019-12-13T17:35:09+05:30 | 2019-12-13T18:16:34+05:30 | I took pull from master to check and resolve issues. | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 2400 |  | 0 | 0m | 0
BIL-284 | Code Review | 0.5 | 2019-12-13T17:47:29+05:30 | 2019-12-13T18:17:39+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 1h 36m | 5760 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-401 | There is no validation that a file can be uploaded only against a document type selected.(Even without selecting document type, if file uploaded, loi entry page opens)) | 0.5 | 2019-12-13T18:33:00+05:30 | 2019-12-18T16:40:34+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 1800 |  | 0 | 0m | 0
BIL-403 | In case of utility and industrial client type, if doc type-'LOI/PPA/PSA' is selected , option to select date and time should be displayed. | 0.42 | 2019-12-13T18:33:15+05:30 | 2019-12-18T16:40:49+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 1500 |  | 0 | 0m | 0
BIL-344 | Release Management | 0.5 | 2019-12-13T23:27:00+05:30 | 2019-12-27T23:56:51+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 1h | 3600 | 30m | 1800 |  | BIL-257 | Manage Contract and Application Summary
BIL-291 | Coding+UT | 6 | 2019-12-16T07:07:00+05:30 | 2019-12-17T13:08:26+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 21600 | 2d | 57600 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-368 | coding+ut | 8 | 2019-12-16T09:30:00+05:30 | 2020-01-06T19:06:47+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 | 2d 30m | 59400 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-426 | add a column to show status of each department on click | 3 | 2019-12-16T09:45:00+05:30 | 2019-12-17T13:46:52+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 10800 |  | 0 | 0m | 0 |  | BIL-255 | Client Registration
BIL-427 | Add pagination to all clients sub module | 4 | 2019-12-16T13:47:00+05:30 | 2019-12-17T13:48:09+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 |  | 0 | 0m | 0 |  | BIL-255 | Client Registration
BIL-414 | On 'Vendor Registration' page,if we click of 'Nodal Rldc Enrolled', page should open in new tab. | 1 | 2019-12-17T00:31:00+05:30 | 2019-12-18T12:31:42+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-291 | Coding+UT | 4 | 2019-12-17T09:08:00+05:30 | 2019-12-17T13:08:37+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 2d | 57600 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-296 | Release Management | 0.5 | 2019-12-17T09:30:00+05:30 | 2019-12-28T00:09:37+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 12m | 720 | 0m | 0 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-413 | On 'Vendor Registration' page, the heading 'General Info', 'Accounts Details' should be shown in Form Legend. | 1 | 2019-12-17T10:00:00+05:30 | 2019-12-18T12:30:26+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-415 | Admin should be assigned the privilege to approve and reject the form. | 1.5 | 2019-12-17T11:05:00+05:30 | 2019-12-18T12:31:05+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 5400 |  | 0 | 0m | 0
BIL-416 | If the form is approved or rejected from the admin end, it should be considered as final approval. | 1 | 2019-12-17T13:42:00+05:30 | 2019-12-18T12:32:12+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-264 | Add Mulitiple Bank Account Details For SLDC | 1.5 | 2019-12-17T15:01:00+05:30 | 2019-12-18T12:33:18+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  | BIL-6 | Vendor Registration | Vendor Registration | Story | 5400 | 3d 3m | 86580 | 0m | 0 | 2019-12-18 | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-434 | Activity Log Not showing on Activity Dashboad | 1 | 2019-12-17T15:30:00+05:30 | 2019-12-18T12:12:37+05:30 | Work with Account team to resolve the issue | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | My Activities |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-346 | Bilateral-Tally Integration | 1.5 | 2019-12-17T18:00:00+05:30 | 2019-12-18T12:17:16+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Story | 5400 |  | 0 | 0m | 0 |  | BIL-346 | Bilateral-Tally Integration
BIL-432 | A 'database error -500' shown on adding LOI import schedule. | 0.42 | 2019-12-17T18:17:56+05:30 | 2019-12-17T18:43:02+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 1500 |  | 0 | 0m | 0
BIL-431 | Document uploaded before LOI creation is not shown in 'LOI Document' section after the entry is done | 0.33 | 2019-12-17T18:23:44+05:30 | 2019-12-17T18:43:49+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 1200 |  | 0 | 0m | 0
BIL-430 | Even when PPA/PSA upload date is mandatory, if without adding date we upload file and proceed, the (PPA/PSA upload date)validation is not working. | 0.42 | 2019-12-17T18:37:51+05:30 | 2019-12-17T19:03:00+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 1500 |  | 0 | 0m | 0
BIL-439 | team review 18 dec 2019 | 3 | 2019-12-18T03:00:00+05:30 | 2020-01-06T19:06:02+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | Project Review |  |  |  |  | Task | 10800 |  | 0 | 0m | 0
BIL-368 | coding+ut | 2 | 2019-12-18T05:00:00+05:30 | 2020-01-06T19:18:35+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 2d 30m | 59400 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-436 | Client integration from lms | 8 | 2019-12-18T09:51:00+05:30 | 2019-12-18T18:51:40+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 28800 |  | 0 | 0m | 0
BIL-288 | Release Management | 0.5 | 2019-12-18T10:00:00+05:30 | 2019-12-28T00:02:43+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 1h 18m | 4680 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-433 | code review | 1.5 | 2019-12-18T10:00:00+05:30 | 2019-12-25T14:20:45+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 5400 | 1h 39m | 5940 | 9m | 540 |  | BIL-361 | revenue data in LMS sheet
BIL-439 | team review 18 dec 2019 | 3 | 2019-12-18T10:00:00+05:30 | 2019-12-25T14:18:43+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | Project Review |  |  |  |  | Task | 10800 |  | 0 | 0m | 0
BIL-370 | project management | 1 | 2019-12-18T10:46:00+05:30 | 2019-12-20T10:46:39+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 1h 24m | 5040 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-435 | Speed Issue | 2 | 2019-12-18T12:23:00+05:30 | 2019-12-25T14:23:16+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | SOP/TDM Bill |  |  |  |  | Bug | 7200 |  | 0 | 0m | 0
BIL-405 | No hard coded constants that could possibly change in the future | 0.5 | 2019-12-18T13:54:00+05:30 | 2019-12-25T14:24:48+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-406 | There is no commented out code | 0.5 | 2019-12-18T13:56:00+05:30 | 2019-12-25T14:25:51+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-407 | There is no commented out code | 0.5 | 2019-12-18T13:57:00+05:30 | 2019-12-25T14:26:44+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-294 | QA Testing | 2 | 2019-12-18T17:29:00+05:30 | 2020-01-03T18:20:22+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 5h 12m | 18720 | 6h | 21600 |  | BIL-263 | Intra- State Wheeling STU , Wheeling and SLDC Operating Charges
BIL-368 | coding+ut | 8 | 2019-12-19T10:00:00+05:30 | 2020-01-06T19:07:21+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 | 2d 30m | 59400 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-402 | invalid permissions. | 0.5 | 2019-12-19T10:00:00+05:30 | 2019-12-25T14:27:36+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-437 | unwanted logs counter | 1 | 2019-12-19T10:13:00+05:30 | 2019-12-19T10:13:37+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 3600 |  | 0 | 0m | 0
BIL-369 | QA Testing | 1 | 2019-12-19T10:42:00+05:30 | 2019-12-20T10:43:15+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 5h 30m | 19800 | 4h 30m | 16200 |  | BIL-361 | revenue data in LMS sheet
BIL-371 | release management | 0.5 | 2019-12-19T10:50:00+05:30 | 2019-12-20T10:51:01+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 1h 24m | 5040 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-302 | QA Testing | 2.6 | 2019-12-19T11:04:00+05:30 | 2019-12-19T18:04:53+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 9360 | 2h 36m | 9360 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges
BIL-373 | Have to update code review detail and description under code review | 1 | 2019-12-19T13:29:00+05:30 | 2019-12-25T14:28:55+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 3600 |  | 0 | 0m | 0
BIL-440 | To check that an option to add 'Inter-state Transmission and Operating Charges' appears state wise. | 0.33 | 2019-12-19T13:32:00+05:30 | 2019-12-27T13:32:53+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Setting |  |  |  |  | Test Case | 1200 |  | 0 | 0m | 0
BIL-441 | To test that there is validation that only numbers are allowed on transmission and operating charges. | 0.33 | 2019-12-19T13:32:00+05:30 | 2019-12-27T13:32:38+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Setting |  |  |  |  | Test Case | 1200 |  | 0 | 0m | 0
BIL-442 | To test that on click of 'Show History' , recently updated charges are shown. | 0.33 | 2019-12-19T13:32:00+05:30 | 2019-12-27T13:32:21+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Setting |  |  |  |  | Test Case | 1200 |  | 0 | 0m | 0
BIL-381 | No Active Sprint found for the task developer working | 0.5 | 2019-12-19T14:07:00+05:30 | 2019-12-25T14:36:43+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-438 | Pending Bugs | 0.5 | 2019-12-19T14:09:00+05:30 | 2019-12-25T14:39:16+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-368 | coding+ut | 8 | 2019-12-20T09:30:00+05:30 | 2020-01-06T19:11:21+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 | 2d 30m | 59400 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-448 | On rejecting a vendor registration form ,remark is a mandatory field. And even after giving remarks, mail notification shows blank remarks. | 0.5 | 2019-12-20T10:01:00+05:30 | 2019-12-20T10:27:04+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 1800 |  | 0 | 0m | 0
BIL-449 | Search is not working | 0.5 | 2019-12-20T11:33:00+05:30 | 2019-12-20T10:33:53+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 1800 |  | 0 | 0m | 0
BIL-278 | QA Testing | 2 | 2019-12-20T15:30:00+05:30 | 2019-12-23T15:30:40+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 1d 2h 36m | 38160 | 2h | 7200 |  | BIL-255 | Client Registration
BIL-270 | QA Testing | 2 | 2019-12-20T15:31:00+05:30 | 2019-12-23T15:31:18+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 5h 18m | 19080 | 1d | 28800 |  | BIL-256 | Change in LOI Entry Module
BIL-444 | On click of 'Show History', empty response . | 0.67 | 2019-12-20T15:48:17+05:30 | 2019-12-27T17:33:54+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Setting |  |  |  |  | Bug | 2400 |  | 0 | 0m | 0
BIL-455 | 'Import Schedule' should be hidden in email in case of 'Add LOI' and should be only shown in case of update LOI. | 0.67 | 2019-12-20T15:48:44+05:30 | 2019-12-27T17:33:29+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 2400 |  | 0 | 0m | 0
BIL-399 | If a file is uploaded in 'LOI Entry' , instead of showing in file viewer, option to download the file appears. | 0.83 | 2019-12-20T15:50:35+05:30 | 2019-12-27T17:34:18+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 3000 |  | 0 | 0m | 0
BIL-456 | UI Issue- Increase the font size of 'Import Schedule' details. | 0.33 | 2019-12-20T15:54:11+05:30 | 2019-12-20T16:14:15+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage LOI |  |  |  |  | Bug | 1200 |  | 0 | 0m | 0
BIL-498 | Add Charges on Trader column in . Revenue and subtract from net Revenue | 8 | 2019-12-23T09:30:00+05:30 | 2020-01-06T19:20:12+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 |  | 0 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-460 | On click of 'Save' on client->All Vendor->Accounts, an error 500occurs. | 3 | 2019-12-23T10:00:00+05:30 | 2019-12-25T23:29:55+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 10800 |  | 0 | 0m | 0
BIL-485 | To check that an option to add 'STU', 'Operating Charges' and 'cross-subsidy' appears state wise. | 0.33 | 2019-12-23T13:18:00+05:30 | 2019-12-27T13:19:05+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Setting |  |  |  |  | Test Case | 1200 |  | 0 | 0m | 0
BIL-278 | QA Testing | 5 | 2019-12-23T13:19:00+05:30 | 2019-12-27T13:20:11+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 18000 | 1d 2h 36m | 38160 | 2h | 7200 |  | BIL-255 | Client Registration
BIL-484 | To check that an option to add 'Injector' and 'Consumer' charges against each voltage level appears state wise. | 0.33 | 2019-12-23T13:19:00+05:30 | 2019-12-27T13:19:19+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | Setting |  |  |  |  | Test Case | 1200 |  | 0 | 0m | 0
BIL-270 | QA Testing | 1 | 2019-12-23T13:20:00+05:30 | 2019-12-27T13:20:53+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 5h 18m | 19080 | 1d | 28800 |  | BIL-256 | Change in LOI Entry Module
BIL-259 | Manage Application | 3.5 | 2019-12-23T15:39:25+05:30 | 2019-12-23T19:09:42+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | Manage Application |  | BIL-129 | Application Status Report | Application Status Report | Story | 12600 | 1w | 144000 | 0m | 0 | 2019-12-31 | BIL-259 | Manage Application
BIL-323 | Coding+UT | 1.33 | 2019-12-23T16:22:00+05:30 | 2019-12-27T17:42:34+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 4800 | 3d | 86400 | 2h | 7200 |  | BIL-259 | Manage Application
BIL-478 | Coding+UT | 6 | 2019-12-24T01:00:00+05:30 | 2019-12-30T10:59:46+05:30 | utr alert settings … | Nitish Kumar | 5daece1baf604e0db364922f | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 21600 | 1d | 28800 | 0m | 0 |  | BIL-475 | Listing Details Min UTR
BIL-461 | Impact Analysis | 0.5 | 2019-12-24T09:30:00+05:30 | 2019-12-26T14:40:33+05:30 |  | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 2h | 7200 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-544 | Change Request by Client | 8 | 2019-12-24T09:31:00+05:30 | 2020-01-07T11:22:21+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 |  | 0 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-463 | Coding+UT | 1 | 2019-12-24T10:00:00+05:30 | 2019-12-26T14:39:15+05:30 | UTR amount will be Check at the Time of Application Punching | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-470 | 'Click Here' link is not working in 'All Vendor'. | 3 | 2019-12-24T10:00:00+05:30 | 2019-12-25T23:19:17+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 10800 |  | 0 | 0m | 0
BIL-463 | Coding+UT | 4 | 2019-12-24T13:30:00+05:30 | 2019-12-26T14:39:44+05:30 | UTR amount will be Check at the Time of Application Punching, working on cron for sending email to account & operation to refill utr | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-323 | Coding+UT | 4 | 2019-12-24T13:42:00+05:30 | 2019-12-27T17:42:49+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 3d | 86400 | 2h | 7200 |  | BIL-259 | Manage Application
BIL-371 | release management | 1 | 2019-12-24T13:56:00+05:30 | 2019-12-26T13:56:27+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 1h 24m | 5040 | 0m | 0 |  | BIL-361 | revenue data in LMS sheet
BIL-323 | Coding+UT | 3.67 | 2019-12-24T14:57:00+05:30 | 2019-12-27T18:38:05+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 13200 | 3d | 86400 | 2h | 7200 |  | BIL-259 | Manage Application
BIL-342 | QA Testing | 2.5 | 2019-12-24T17:44:00+05:30 | 2019-12-27T17:44:42+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 9000 | 2h 36m | 9360 | 0m | 0 |  | BIL-257 | Manage Contract and Application Summary
BIL-286 | QA Testing | 3.5 | 2019-12-24T18:09:00+05:30 | 2020-01-03T18:09:48+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 12600 | 5h 18m | 19080 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-471 | On click of 'Approve', an error 500 shows. | 3 | 2019-12-24T20:14:00+05:30 | 2019-12-25T23:14:00+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 10800 |  | 0 | 0m | 0
BIL-542 | Coding+UT | 8 | 2019-12-26T09:30:00+05:30 | 2020-01-07T11:32:31+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 |  | 0 | 0m | 0 |  | BIL-541 | RLDC Payment Report
BIL-463 | Coding+UT | 6.5 | 2019-12-26T09:30:00+05:30 | 2019-12-26T18:14:04+05:30 | cron for sending email to account & operation to refill utr, Notification of Unused UTR on every 15 days for older than 2 month& Previous Financial Year to Operation Team, working on utr alert module design | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 23400 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-323 | Coding+UT | 5 | 2019-12-26T13:38:00+05:30 | 2019-12-27T18:38:15+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 18000 | 3d | 86400 | 2h | 7200 |  | BIL-259 | Manage Application
BIL-463 | Coding+UT | 0.75 | 2019-12-26T17:30:00+05:30 | 2019-12-26T18:13:40+05:30 | utr alert module | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 2700 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-453 | There is no commented out code | 0.17 | 2019-12-27T03:30:00+05:30 | 2020-01-06T19:00:40+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 600 |  | 0 | 0m | 0
BIL-492 | Transaction not showing two times if transaction have both bill (SOP,TDM) | 4 | 2019-12-27T09:30:00+05:30 | 2020-01-06T19:00:08+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | SOP/TDM Bill |  |  |  |  | Bug | 14400 |  | 0 | 0m | 0
BIL-463 | Coding+UT | 1 | 2019-12-27T09:30:00+05:30 | 2019-12-28T10:54:22+05:30 | check code for unused utr | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-339 | Coding+UT | 1 | 2019-12-27T10:30:00+05:30 | 2019-12-31T15:54:16+05:30 | Deviation In Contract | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 1d | 28800 | 5h | 18000 |  | BIL-257 | Manage Contract and Application Summary
BIL-286 | QA Testing | 7 | 2019-12-27T10:38:00+05:30 | 2020-01-03T18:21:59+05:30 |  | Shalini Kumari | 5c6fb86bef824a130638ddba | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 25200 | 5h 18m | 19080 | 0m | 0 |  | BIL-264 | Add Mulitiple Bank Account Details For SLDC
BIL-488 | If without entering any details and without selecting checkbox, if we click on 'Submit', a entry with account no.0 is created. | 1 | 2019-12-27T10:38:00+05:30 | 2019-12-28T10:39:02+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-329 | Impact Analysis | 1 | 2019-12-27T11:16:00+05:30 | 2019-12-28T12:16:33+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 2h | 7200 | 1h | 3600 |  | BIL-258 | Manaual Application / Provisional
BIL-489 | On click of delete, the row for bank details is not deleted, even after alert of success message. | 1 | 2019-12-27T11:40:00+05:30 | 2019-12-28T10:40:55+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | Manage Client |  |  |  |  | Bug | 3600 |  | 0 | 0m | 0
BIL-339 | Coding+UT | 1.5 | 2019-12-27T12:00:00+05:30 | 2019-12-31T15:53:26+05:30 | Deviation In Contract | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 5400 | 1d | 28800 | 5h | 18000 |  | BIL-257 | Manage Contract and Application Summary
BIL-459 | On updating 'vendor profile', short code already message alert. | 1 | 2019-12-27T12:43:00+05:30 | 2019-12-28T10:43:56+05:30 |  | Mohd Imran | 5daeb10ad87cf10da3e0c327 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 3600 |  | 0 | 0m | 0
BIL-454 | No hard coded constants that could possibly change in the future | 0.5 | 2019-12-27T13:30:00+05:30 | 2020-01-06T18:59:28+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-452 | The code is easy to understand | 0.5 | 2019-12-27T14:00:00+05:30 | 2020-01-06T18:58:54+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-323 | Coding+UT | 3.5 | 2019-12-27T14:14:00+05:30 | 2019-12-27T17:44:33+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 12600 | 3d | 86400 | 2h | 7200 |  | BIL-259 | Manage Application
BIL-323 | Coding+UT | 2 | 2019-12-27T14:38:57+05:30 | 2019-12-28T12:13:48+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 | 3d | 86400 | 2h | 7200 |  | BIL-259 | Manage Application
BIL-339 | Coding+UT | 0.5 | 2019-12-27T16:30:00+05:30 | 2019-12-31T15:53:50+05:30 | Deviation In Contract | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 1d | 28800 | 5h | 18000 |  | BIL-257 | Manage Contract and Application Summary
BIL-345 | UTR state charges settings. | 1 | 2019-12-27T17:00:00+05:30 | 2019-12-31T15:55:51+05:30 |  | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | UTR |  | BIL-22 | UTR Setting | UTR Setting | Story | 3600 | 4d 7h 50m | 143400 | 0m | 0 | 2019-12-31 | BIL-345 | UTR state charges settings.
BIL-321 | Impact Analysis | 1 | 2019-12-27T17:31:10+05:30 | 2019-12-27T18:31:15+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 3600 | 2h | 7200 | 0m | 0 |  | BIL-259 | Manage Application
BIL-542 | Coding+UT | 8 | 2019-12-30T09:30:00+05:30 | 2020-01-07T11:33:03+05:30 |  | Adarsh Kumar | 5c762c93d48a17049c3aeebb | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 28800 |  | 0 | 0m | 0 |  | BIL-541 | RLDC Payment Report
BIL-463 | Coding+UT | 0.5 | 2019-12-30T09:30:00+05:30 | 2019-12-31T09:45:50+05:30 | cron for Advance auto alert for Bank Holiday to refill the UTR as per the History of Used UTR | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 1800 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-325 | Estimation | 2 | 2019-12-30T10:00:00+05:30 | 2020-01-06T13:16:36+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-259 | Manage Application
BIL-465 | Estimation | 2 | 2019-12-30T10:17:00+05:30 | 2020-01-06T12:17:39+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-543 | Project Management | 2 | 2019-12-30T10:40:00+05:30 | 2020-01-07T10:40:44+05:30 |  | Ashish Gupta | 5c762c3bcf74864794a37e6a | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-541 | RLDC Payment Report
BIL-333 | Estimation | 2 | 2019-12-30T11:20:00+05:30 | 2020-01-06T13:20:11+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 7200 |  | 0 | 0m | 0 |  | BIL-258 | Manaual Application / Provisional
BIL-463 | Coding+UT | 2.5 | 2019-12-30T11:30:00+05:30 | 2019-12-31T09:46:13+05:30 | cron for Advance auto alert for Bank Holiday to refill the UTR as per the History of Used UTR | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 9000 | 3d | 86400 | 0m | 0 |  | BIL-345 | UTR state charges settings.
BIL-535 | There is no commented out code | 0.5 | 2019-12-30T16:09:00+05:30 | 2020-01-06T16:39:26+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-534 | There is no commented out code | 0.5 | 2019-12-30T16:10:00+05:30 | 2020-01-06T16:40:14+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-533 | No code that can be replaced with library functions | 0.5 | 2019-12-30T16:13:00+05:30 | 2020-01-06T16:43:59+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Bug | 1800 |  | 0 | 0m | 0
BIL-331 | Coding+UT | 4 | 2019-12-31T06:42:00+05:30 | 2020-01-03T10:43:11+05:30 |  | Manas Khurana | 5daeb1285304a60c3a763763 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 14400 | 3d | 86400 | 0m | 0 |  | BIL-258 | Manaual Application / Provisional
BIL-345 | UTR state charges settings. | 1.5 | 2019-12-31T10:00:00+05:30 | 2019-12-31T16:18:30+05:30 |  | kirti.arya | 5de50c9fde32fb0d03a3b565 | BIL | Bilateral Kreate -Enhancement | UTR |  | BIL-22 | UTR Setting | UTR Setting | Story | 5400 | 4d 7h 50m | 143400 | 0m | 0 | 2019-12-31 | BIL-345 | UTR state charges settings.
BIL-301 | Estimation | 3 | 2019-12-31T13:29:00+05:30 | 2020-01-06T16:30:32+05:30 |  | Shantanu Sharma | 5de4e1117095a40d12539178 | BIL | Bilateral Kreate -Enhancement | [5 empty] | Sub-task | 10800 |  | 0 | 0m | 0 |  | BIL-262 | Inter - State Transmission and Operating Charges